## Identity
Internal contract management snapshot | SYNTHETIC amended and corrected management position
Issued | 2026-09-08T07:35:19.046704+00:00
Contract | SYNTHETIC planning contract
Project ID | 119daca9-be3d-43bc-92a8-9fe90e95f445
Contract ID | fed59a17-4e87-4dca-9204-2d2cc0f8420e
As of | 2026-09-08
Source cutoff | 2026-09-08T07:35:18.909+00:00
Original approved baseline | 563edebd-6b1e-47b8-a401-f3556661a15b
Current approved baseline | 2c70ec62-cbf7-408f-8a47-ab43f1e2408f
Baseline hash | 8edf2557b2e12e24961b2d19f6af06ba5629c694ee07342ebe9ce1aab924194f
Snapshot ID | 10743383-1fb0-42c4-8f85-5530840f8c54
Snapshot hash | 7c7fea8f27a73573e4673a72c90b45fe900504573f23705df8572ed8fffac85e
Currency | USD
Coverage evidence | SYNTHETIC engineering assignment only. Original and amended baselines retained; August opening excludes all September detail. Approved labor, nonbillable rework, CSV expense, partial payment, credit and commitment reconcile. Remaining estimates inclu
de future commitments once. No real authority or external accounting acceptance.
Coverage attestation | Complete source coverage attested by issuer
Meaning | Internal management. No accounting replacement, funder reimbursement, legal authority, accepted progress or forecast finish date is established.

## Contract totals
Work | incurred | commitments | payments | credits | hours
Contract | 249.5 | 100 | 75 | 10 | 4.8

## Tasks
Work | incurred | commitments | payments | credits | hours
Draft analysis | 181.5 | 0 | 75 | 10 | 3.32
Review | 68 | 100 | 0 | 0 | 1.48

## Staff
Work | incurred | commitments | payments | credits | hours
SYNTHETIC planner | 185.5 | 0 | 0 | 0 | 3.2
No staff attribution | 40 | 100 | 75 | 10 | 1
SYNTHETIC analyst | 24 | 0 | 0 | 0 | 0.6

## Deliverables
Work | incurred | commitments | payments | credits | hours
SYNTHETIC planning report | 249.5 | 100 | 75 | 10 | 4.8

## Budget and billing
Measure | Amount
Approved fee | 1200
Approved internal cost | 600
Gross billed before retention | 200
Invoice retention | 20
Gross fee remaining after credits | 1010
Remaining cost estimate | 400
Actual plus remaining | 649.5
Unknown historical hours | 0

## Baseline history
Version | State | Identity | Scope | Fee | Cost | Hours | Approval evidence | Source documents | Hash
1 | approved | 563edebd-6b1e-47b8-a401-f3556661a15b | Synthetic planning report, draft analysis and review. Engineering acceptance only. | 1000 | 500 | 10 | SYNTHETIC test owner records approval of original agreement for engineering acceptance only. No real contractual authority. | 4d9374f4-f233-49fe-b76f-33d6ea4c373d | 40d3ad854646989f9e287d3d63af8433899f521fbfc569ed4ac607a60709f6f9
2 | approved | 2c70ec62-cbf7-408f-8a47-ab43f1e2408f | Synthetic scope amendment adds follow-up review. Test approval only, no real authority. | 1200 | 600 | 12 | SYNTHETIC amendment approval: fee increases to USD 1,200 gross before retention, internal budget to USD 600 and hours to 12. Review task gains USD 200 fee, USD 100 cost and 2 hours. Engineering test only; no real contractual authority. | 4d9374f4-f233-49fe-b76f-33d6ea4c373d | 8edf2557b2e12e24961b2d19f6af06ba5629c694ee07342ebe9ce1aab924194f

## Remaining work
Task | Agreed deadline | Estimate date | Remaining hours | Remaining cost | Estimate basis | Independent progress | Progress note
Draft analysis | 2026-10-01 | 2026-09-08 | 4.8 | 240 | Synthetic amendment review: remaining draft scope requires 4.80 hours at documented internal assumptions. Incurred opening, time and expense are excluded. | 25 | Synthetic report sections independently assessed, awaiting review. Expenditure is not progress or a finish date.
Review | 2026-10-08 | 2026-09-08 | 3.2 | 160 | Synthetic remaining review estimate includes the 100.00 future commitment; commitments are disclosed separately and must not be added again. | 25 | Synthetic report sections independently assessed, awaiting review. Expenditure is not progress or a finish date.

## Source history
Source | Version | Recorded | Date | Category | Status | Amount | Hours | Reference | Correction | Physical source | OWP version
SYNTH-TIME-001 | 1 | 2026-09-08T06:45:29.01443+00:00 | 2026-09-01 | labor | draft | Unassessed | 2 | SYNTHETIC time ledger row 001 |  | 6604b73a-5168-43b2-b7af-0fd051ede41f | Unassessed
SYNTH-TIME-001 | 2 | 2026-09-08T06:46:07.16141+00:00 | 2026-09-01 | labor | approved | 100 | 2 | SYNTHETIC time ledger row 001 | SYNTHETIC time approved at the retained effective cost rate. | 6604b73a-5168-43b2-b7af-0fd051ede41f | Unassessed
SYNTH-REWORK-001 | 1 | 2026-09-08T06:59:05.802136+00:00 | 2026-09-03 | labor | approved | 50 | 1 | SYNTHETIC time ledger nonbillable rework |  | 2bc73cf6-9cf6-4c77-b322-8dcc1b590616 | Unassessed
SYNTH-EXP-001 | 1 | 2026-09-08T07:01:58.589536+00:00 | 2026-09-04 | expense | draft | 25.5 | Unassessed | SYNTHETIC-expenses.csv; sha256:f59cce2e0baca534d7ec720614e7a9fecc34ccd8ecc61b4317b82327c5c29be2; CSV row 1; SYNTHETIC expense intake, no actual spending. |  | 614d277d-a586-4761-94f0-43593a803028 | Unassessed
SYNTH-EXP-001 | 2 | 2026-09-08T07:02:40.265101+00:00 | 2026-09-04 | expense | approved | 25.5 | Unassessed | SYNTHETIC-expenses.csv; sha256:f59cce2e0baca534d7ec720614e7a9fecc34ccd8ecc61b4317b82327c5c29be2; CSV row 1; SYNTHETIC expense intake, no actual spending. | SYNTHETIC receipt checked and allocated to draft analysis. | 614d277d-a586-4761-94f0-43593a803028 | Unassessed
SYNTH-TIME-001 | 3 | 2026-09-08T07:05:35.944489+00:00 | 2026-09-01 | labor | approved | 110 | 2.2 | SYNTHETIC time ledger row 001 | SYNTHETIC payroll correction adds 0.20 hours. Original issued invoice and snapshot remain retained; no new billing event implied. | 6604b73a-5168-43b2-b7af-0fd051ede41f | Unassessed
SYNTH-PAY-001 | 1 | 2026-09-08T07:14:46.228357+00:00 | 2026-09-08 | payment | approved | 75 | Unassessed | SYNTHETIC bank receipt, engineering only; 75.00 partial payment against SYNTH-INV-001. |  | Unassessed | Unassessed
SYNTH-CREDIT-001 | 1 | 2026-09-08T07:19:51.547763+00:00 | 2026-09-08 | credit | approved | 10 | Unassessed | SYNTHETIC documented credit memo 10.00 against SYNTH-INV-001; does not reverse incurred work. |  | Unassessed | Unassessed
SYNTH-MEMBER-001 | 1 | 2026-09-08T07:27:16.317129+00:00 | 2026-09-07 | labor | draft | Unassessed | 0.5 | SYNTHETIC analyst timesheet, engineering acceptance only. |  | a6402ece-f1d8-48f0-b6d8-a4a4af0c1add | Unassessed
SYNTH-MEMBER-001 | 2 | 2026-09-08T07:29:05.812842+00:00 | 2026-09-07 | labor | draft | Unassessed | 0.6 | SYNTHETIC analyst timesheet, engineering acceptance only. | Synthetic draft typo correction, 36 minutes. | a6402ece-f1d8-48f0-b6d8-a4a4af0c1add | Unassessed
SYNTH-MEMBER-001 | 3 | 2026-09-08T07:30:00.483469+00:00 | 2026-09-07 | labor | approved | 24 | 0.6 | SYNTHETIC analyst timesheet; approved private payroll amount 24.00 for 0.60 hours, engineering only. | Owner review of synthetic analyst payroll evidence. | a6402ece-f1d8-48f0-b6d8-a4a4af0c1add | Unassessed
SYNTH-OPENING-001 | 1 | 2026-09-08T07:33:32.111552+00:00 | 2026-08-31 | opening | approved | 40 | 1 | SYNTHETIC predecessor ledger closing balance, August 2026, cost 40.00 and one historical hour. |  | Unassessed | Unassessed
SYNTH-COMMITMENT-001 | 1 | 2026-09-08T07:34:07.351967+00:00 | 2026-09-08 | commitment | approved | 100 | Unassessed | SYNTHETIC purchase commitment 100.00 for future review support. No incurred cost or payment. |  | Unassessed | Unassessed

## Allocations
Source | Version | Task | Deliverable | Share (basis points) | Amount | Hours
SYNTH-TIME-001 | 1 | d8e0035d-6052-4289-9b74-38fd7ce53719 | 56d649b1-9cc8-4797-b993-b6fee2bcba71 | 6000 | Unassessed | 1.2
SYNTH-TIME-001 | 1 | bdb33246-09da-42b1-b13d-0e9553d90f2c | 56d649b1-9cc8-4797-b993-b6fee2bcba71 | 4000 | Unassessed | 0.8
SYNTH-TIME-001 | 2 | d8e0035d-6052-4289-9b74-38fd7ce53719 | 56d649b1-9cc8-4797-b993-b6fee2bcba71 | 6000 | 60 | 1.2
SYNTH-TIME-001 | 2 | bdb33246-09da-42b1-b13d-0e9553d90f2c | 56d649b1-9cc8-4797-b993-b6fee2bcba71 | 4000 | 40 | 0.8
SYNTH-REWORK-001 | 1 | d8e0035d-6052-4289-9b74-38fd7ce53719 | 56d649b1-9cc8-4797-b993-b6fee2bcba71 | 10000 | 50 | 1
SYNTH-EXP-001 | 1 | d8e0035d-6052-4289-9b74-38fd7ce53719 | 56d649b1-9cc8-4797-b993-b6fee2bcba71 | 10000 | 25.5 | Unassessed
SYNTH-EXP-001 | 2 | d8e0035d-6052-4289-9b74-38fd7ce53719 | 56d649b1-9cc8-4797-b993-b6fee2bcba71 | 10000 | 25.5 | Unassessed
SYNTH-TIME-001 | 3 | d8e0035d-6052-4289-9b74-38fd7ce53719 | 56d649b1-9cc8-4797-b993-b6fee2bcba71 | 6000 | 66 | 1.32
SYNTH-TIME-001 | 3 | bdb33246-09da-42b1-b13d-0e9553d90f2c | 56d649b1-9cc8-4797-b993-b6fee2bcba71 | 4000 | 44 | 0.88
SYNTH-PAY-001 | 1 | d8e0035d-6052-4289-9b74-38fd7ce53719 | 56d649b1-9cc8-4797-b993-b6fee2bcba71 | 10000 | 75 | Unassessed
SYNTH-CREDIT-001 | 1 | d8e0035d-6052-4289-9b74-38fd7ce53719 | 56d649b1-9cc8-4797-b993-b6fee2bcba71 | 10000 | 10 | Unassessed
SYNTH-MEMBER-001 | 1 | bdb33246-09da-42b1-b13d-0e9553d90f2c | 56d649b1-9cc8-4797-b993-b6fee2bcba71 | 10000 | Unassessed | 0.5
SYNTH-MEMBER-001 | 2 | bdb33246-09da-42b1-b13d-0e9553d90f2c | 56d649b1-9cc8-4797-b993-b6fee2bcba71 | 10000 | Unassessed | 0.6
SYNTH-MEMBER-001 | 3 | bdb33246-09da-42b1-b13d-0e9553d90f2c | 56d649b1-9cc8-4797-b993-b6fee2bcba71 | 10000 | 24 | 0.6
SYNTH-OPENING-001 | 1 | d8e0035d-6052-4289-9b74-38fd7ce53719 | 56d649b1-9cc8-4797-b993-b6fee2bcba71 | 10000 | 40 | 1
SYNTH-COMMITMENT-001 | 1 | bdb33246-09da-42b1-b13d-0e9553d90f2c | 56d649b1-9cc8-4797-b993-b6fee2bcba71 | 10000 | 100 | Unassessed

## Unresolved
Record | State | Known amount | Known hours

## Approved task budgets
Task | Fee | Internal cost | Hours | Agreed deadline | Scope
Draft analysis | 600 | 300 | 6 | 2026-10-01 | Draft synthetic report. Task budget is staff effort only.
Review | 600 | 300 | 6 | 2026-10-08 | Review synthetic report. Staff effort only.

## Approved staff budgets
Task | Staff | Hours | Internal cost
Draft analysis | SYNTHETIC planner | 6 | 300
Review | SYNTHETIC planner | 6 | 300

## Billing source allocations
Invoice | Source entry | Valuation version | Billing rate | Task | Deliverable | Gross fee | Hours
d34600dd-aff8-43a4-943d-414e91a1ed5c | e7468ac6-c01e-4128-a4ad-593560ae3655 | 1a655228-37d0-45d9-b2d2-f4cbcc99ae41 | ecd513ee-ffef-43d9-b6dc-b61420723006 | d8e0035d-6052-4289-9b74-38fd7ce53719 | 56d649b1-9cc8-4797-b993-b6fee2bcba71 | 120 | 1.2
d34600dd-aff8-43a4-943d-414e91a1ed5c | e7468ac6-c01e-4128-a4ad-593560ae3655 | 1a655228-37d0-45d9-b2d2-f4cbcc99ae41 | ecd513ee-ffef-43d9-b6dc-b61420723006 | bdb33246-09da-42b1-b13d-0e9553d90f2c | 56d649b1-9cc8-4797-b993-b6fee2bcba71 | 80 | 0.8

## Valuation evidence
Source | Version | Basis | Cost rate | Opening coverage | Opening basis | Overlap reconciliation | Shared source state
SYNTH-TIME-001 | 1 | unvalued | Unassessed | to |  |  | Retained valuation
SYNTH-TIME-001 | 2 | cost_rate | 3b0dd867-6420-4058-90f1-31b491fde76d | to |  |  | Retained valuation
SYNTH-REWORK-001 | 1 | cost_rate | 3b0dd867-6420-4058-90f1-31b491fde76d | to |  |  | Retained valuation
SYNTH-EXP-001 | 1 | recorded | Unassessed | to |  |  | Retained valuation
SYNTH-EXP-001 | 2 | recorded | Unassessed | to |  |  | Retained valuation
SYNTH-TIME-001 | 3 | cost_rate | 3b0dd867-6420-4058-90f1-31b491fde76d | to |  |  | Retained valuation
SYNTH-PAY-001 | 1 | recorded | 3b0dd867-6420-4058-90f1-31b491fde76d | to |  |  | Retained valuation
SYNTH-CREDIT-001 | 1 | recorded | Unassessed | to |  |  | Retained valuation
SYNTH-MEMBER-001 | 1 | unvalued | Unassessed | to |  |  | Retained valuation
SYNTH-MEMBER-001 | 2 | unvalued | Unassessed | to |  |  | Retained valuation
SYNTH-MEMBER-001 | 3 | recorded | Unassessed | to |  |  | Retained valuation
SYNTH-OPENING-001 | 1 | recorded | Unassessed | 2026-08-01 to 2026-08-31 | Documented synthetic incurred internal cost through August 31. Excludes all September time and spending; no payment or billing is inferred. |  | Retained valuation
SYNTH-COMMITMENT-001 | 1 | recorded | Unassessed | to |  |  | Retained valuation

## Rates
Staff | Basis | Effective start | Effective end | Rate | Source | Identity
SYNTHETIC planner | cost | 2026-01-01 | 2026-12-31 | 50 | SYNTHETIC approved internal payroll cost schedule, engineering only. | 3b0dd867-6420-4058-90f1-31b491fde76d
SYNTHETIC planner | billing | 2026-01-01 | 2026-12-31 | 100 | SYNTHETIC agreement billing schedule, USD 100 per hour. | ecd513ee-ffef-43d9-b6dc-b61420723006

## Agreement evidence
Baseline | Document | Title | SHA-256 | Retained file | Bytes
563edebd-6b1e-47b8-a401-f3556661a15b | 4d9374f4-f233-49fe-b76f-33d6ea4c373d | SYNTHETIC contract agreement, engineering only | 8dbe0a8bc83dded42ffade46605165439a5a3787f10375ecb99c09aaab78c18c | storage://kb-documents/0ccb6da6-c9e4-42f3-9a5f-833e8835ebdf/4d9374f4-f233-49fe-b76f-33d6ea4c373d/SYNTHETIC-agreement.txt | 454
2c70ec62-cbf7-408f-8a47-ab43f1e2408f | 4d9374f4-f233-49fe-b76f-33d6ea4c373d | SYNTHETIC contract agreement, engineering only | 8dbe0a8bc83dded42ffade46605165439a5a3787f10375ecb99c09aaab78c18c | storage://kb-documents/0ccb6da6-c9e4-42f3-9a5f-833e8835ebdf/4d9374f4-f233-49fe-b76f-33d6ea4c373d/SYNTHETIC-agreement.txt | 454

## Staff budget coverage
Task | Cost not allocated to staff | Hours not allocated to staff | Unknown staff costs | Unknown staff hours | Meaning
Draft analysis | 0 | 0 | 0 | 0 | Difference from known staff allocations. May include direct expenses; consult the retained task scope.
Review | 0 | 0 | 0 | 0 | Difference from known staff allocations. May include direct expenses; consult the retained task scope.